## Product Backlog
ID | User Stories/Technical Requirements | Points
1 | Create databases on MySQL | 1
2 | As a customer, I would like the films to be displayed, so that i can select the films that appeal to me | 8
3 | As a customer, I would like to be able to buy tickets, so that I can watch movies | 10
4 | As a customer, I would like to register for an account, so that I can use it to make my transactions | 2
5 | As a customer, I would like there to be a login option, so i can easily access my account | 1
6 | As a customer, I want there to be a sign out option, so that i can exit my session. | 1
7 | As a customer, I would like to select my seat/seats, so that i know where i will sit when i enter the screening room. | 8
8 | As a customer, I want to have a payment selection section, so that i can pay for my tickets | 10
9 | As customer, I would like to have a booking confirmation displayed, so that I am assured that the payment has gone through the system. | 5
10 | As a customer, I would like to post and edit reviews as well as see reviews from other viewers, so that I can inform other users who may be wanting to watch the movie and to decide on whether a movie appeals to me or not. | 3
11 | As a customer I would like to be able to see the booking history of the tickets, so that i can see what tickets i've previously purchased. | 2
12 | As a customer, I would like to be able to view a trending page that shows a user the current trending movies for a week, so that they can make their selection easier. | 5
13 | As a customer, I would like to use discount codes, so that i can get a percentage off a movie ticket. | 1

## Group C2-3 Sprint 3
User Stories/Technical Requirement | Points | Tasks | Team member | Sprint duration (15/02 - 12/03)
|  |  |  | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08
As customer, I would like to have a booking confirmation displayed, so that I am assured that the payment has gone through the system. | 5 | Create a booking page(1) | Evgeni
|  | Message that includes all the booking details (database retrieval)(2) | Amit
|  | Allow all users to manage their bookings(2) | Kezia/Sukh
As a customer, I would like to post and edit reviews as well as see reviews from other viewers, so that I can inform other users who may be wanting to watch the movie and to decide on whether a movie appeals to me or not. | 3 | Create a review page(0.5) | Kezia
|  | Add a post button that will upload a user review(1.5) | Sukh
|  | Add an edit button so that a user can change a review(1) | Sukh
As a customer I would like to be able to see the booking history of the tickets so that i can see what tickets i've previously purchased. | 2 | Create a booking history page(0.5) | Amit
|  | Retrieve booking number from database to show booking confirmation(1.5) | Evgeni
|  |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12