## Product Backlog
ID | User Stories/Technical Requirements | Points
1 | Create databases on MySQL | 1
2 | As a customer, I would like the films to be displayed, so that i can select the films that appeal to me | 8
3 | As a customer, I would like to be able to buy tickets, so that I can watch movies | 10
4 | As a customer, I would like to register for an account, so that I can use it to make my transactions | 2
5 | As a customer, I would like there to be a login option, so i can easily access my account | 1
6 | As a customer, I want there to be a sign out option, so that i can exit my session. | 1
7 | As a customer, I would like to select my seat/seats, so that i know where i will sit when i enter the screening room. | 8
8 | As a customer, I want to have a payment selection section, so that i can pay for my tickets | 10
9 | As customer, I would like to have a booking confirmation displayed, so that I am assured that the payment has gone through the system. | 5
10 | As a customer, I would like to post and edit reviews as well as see reviews from other viewers, so that I can inform other users who may be wanting to watch the movie and to decide on whether a movie appeals to me or not. | 3
11 | As a customer I would like to be able to see the booking history of the tickets, so that i can see what tickets i've previously purchased. | 2
12 | As a customer, I would like to be able to view a trending page that shows a user the current trending movies for a week, so that they can make their selection easier. | 5
13 | As a customer, I would like to use discount codes, so that i can get a percentage off a movie ticket. | 1

## Group C2-3 Sprint 1
User Stories/Technical Requirement | Tasks | Sprint duration (25/01 - 12/02)
|  | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12
Create databases on MySQL [1 point] | Create a database to store the user details (forename, surname, email, password) [0.25] | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create a database to store the Ticket stock (film, time, stock) [0.25] | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create a database to store the data of available seats (seat number, time, availability) [0.25] | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create a database to store the booking information (film, time, seat, booking number) [0.25] | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a customer i would like the films to be displayed, so that i can select the films that appeal to me [8 points] | Display the image and title underneath for each movie (repeat 4-5 times) [1] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Redirect to movie info page when image is clicked [2] | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add image and description of movie into the movie info page [1] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add a button 'buy tickets' that redirects to the ticket selection page when clicked [2] | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add a button 'reviews' that redirects to the reviews page when clicked [2] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a customer I would like to be able to buy tickets so that I can watch movies [10 points] | Access the ticket stock database and check the availability [3] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Display 'sold out' if no tickets are available [1] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create a drop down box so the user can select from the available screening time [3] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Display the available ticket options and prices [3] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
As a customer i would like to register for an account so that I can use it to make my transactions [2 points] | Create a registration form that asks for forename, surname, email, password [0.5] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
| Validate the fields (check if they are filled and the email and password meet criteria) [0.5] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
| Upload the field data to the user details database [1] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
As a customer i would like there to be a login option so i can easily access my account [1 point] | Create a login form that asks for a valid email and password [0.5] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| Validate the login fields (check if both are filled + if they match the details in the users database) [0.5] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
As a customer I want there to be a sign out option so that i can exit my session [1 point] | Create the sign out button that terminates the user session when clicked [0.5] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
| Redirect to the home page [0.5] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
|  | 23 | 22 | 21 | 19 | 18 | 16 | 14 | 12 | 11 | 10 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0

## Group C2-3 Sprint 2
User Stories/Technical Requirement | Points | Tasks | Team member | Sprint duration (15/02 - 12/03)
|  |  |  | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27 | 2021-02-28 | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12
As a customer I would like to be able to buy tickets, so that I can watch movies [10 points] | 10 | Access the ticket stock database and check the availability [3] | Amit | 2021-02-23: 1; 2021-02-27: 2
|  | Display 'sold out' if no tickets are available [1] | Kezia | bar: 2021-02-21
|  | Create a drop down box so the user can select from the available screening time [3] | Evgeni | bar: 2021-02-18; 2021-02-20 to 2021-02-21
|  | Display the available ticket options and prices [3] | Evgeni | 2021-02-16: 1; 2021-02-17: 2
As a customer i would like to select my seat/seats so that i know where i will sit when i enter the screening room [10 points] | 10 | Create a seats page [2] | Sukh | 2021-02-26: 2
|  | Check the seat availability by comparing to the table [2.5] | Amit | 2021-02-28: 1; 2021-03-02: 1.5
|  | Use AJAX to turn the seat green /red(availability) [4] | Evgeni/Amit | 2021-03-11: 2; 2021-03-12: 2
|  | Proceed button that redirects to payment page [0.5] | Kezia | 2021-03-08: 0.5
|  | Update the seat table with the availability and update the booking page with the seat number [1] | Amit | bar: 2021-03-09
As a customer i want to have a payment selection section so that i can pay for my tickets [6 points] | 6 | Create payment page [1] | Kezia | bar: 2021-03-01
|  | Validate payment input fields [1.5] | Sukh/Kezia | 2021-03-03: 1; 2021-03-04: 0.5
|  | Create table with the information inputted [3] | Evgeni | 2021-03-05: 2; 2021-03-06: 1
|  | Proceed to the booking confirmation [0.5] | Sukh | 2021-03-06: 0.5
|  |  |  | 26 | 25 | 23 | 22 | 22 | 21 | 19 | 19 | 18 | 18 | 18 | 16 | 14 | 13 | 12 | 10.5 | 9.5 | 9 | 7 | 5.5 | 5.5 | 5 | 4 | 4 | 2 | 0

## Group C2-3 Sprint 3
User Stories/Technical Requirement | Points | Tasks | Team member | Sprint duration (15/02 - 12/03)
|  |  |  | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08
As customer, I would like to have a booking confirmation displayed, so that I am assured that the payment has gone through the system. | 5 | Create a booking page(1) | Evgeni | bar: 2021-03-22
|  | Message that includes all the booking details (database retrieval)(2) | Amit | 2021-03-24: 2
|  | Allow all users to manage their bookings(2) | Kezia/Sukh | bar: 2021-03-26 to 2021-03-27
As a customer, I would like to post and edit reviews as well as see reviews from other viewers, so that I can inform other users who may be wanting to watch the movie and to decide on whether a movie appeals to me or not. | 3 | Create a review page(0.5) | Kezia | 2021-03-29: 0.5
|  | Add a post button that will upload a user review(1.5) | Sukh
|  | Add an edit button so that a user can change a review(1) | Sukh
As a customer I would like to be able to see the booking history of the tickets so that i can see what tickets i've previously purchased. | 2 | Create a booking history page(0.5) | Amit
|  | Retrieve booking number from database to show booking confirmation(1.5) | Evgeni
|  |  |  | 11 | 11 | 9 | 9 | 8 | 7 | 7 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5